## orders
order_id | customer | product | category | pieces | order_date | due_date | status | current_stage | last_activity_date | completed_date | days_late
ORD-057 | UrbanThread | Cardigan | TOPS | 600 | 2026-01-01 | 2026-02-02 | COMPLETE | COMPLETE | 2026-01-25 | 2026-01-25 | -8
ORD-076 | TrendCart | Crewneck sweater | TOPS | 1200 | 2026-01-02 | 2026-01-27 | COMPLETE | COMPLETE | 2026-02-08 | 2026-02-08 | 12
ORD-110 | Cotton Club | Scarf | ACCESSORIES | 600 | 2026-01-02 | 2026-01-24 | COMPLETE | COMPLETE | 2026-01-27 | 2026-01-27 | 3
ORD-025 | Cotton Club | Scarf | ACCESSORIES | 400 | 2026-01-03 | 2026-01-26 | COMPLETE | COMPLETE | 2026-01-23 | 2026-01-23 | -3
ORD-077 | UrbanThread | Hoodie | TOPS | 1000 | 2026-01-03 | 2026-02-07 | COMPLETE | COMPLETE | 2026-01-29 | 2026-01-29 | -9
ORD-087 | TrendCart | Hoodie | TOPS | 1000 | 2026-01-03 | 2026-01-19 | COMPLETE | COMPLETE | 2026-02-18 | 2026-02-18 | 30
ORD-091 | TrendCart | Polo shirt | TOPS | 600 | 2026-01-03 | 2026-02-02 | COMPLETE | COMPLETE | 2026-01-27 | 2026-01-27 | -6
ORD-117 | Cotton Club | Scarf | ACCESSORIES | 1000 | 2026-01-04 | 2026-01-18 | COMPLETE | COMPLETE | 2026-02-02 | 2026-02-02 | 15
ORD-007 | Harbor Knits | Cardigan | TOPS | 2000 | 2026-01-06 | 2026-01-30 | COMPLETE | COMPLETE | 2026-02-13 | 2026-02-13 | 14
ORD-080 | Bright Basics | Hoodie | TOPS | 2000 | 2026-01-07 | 2026-01-30 | COMPLETE | COMPLETE | 2026-02-18 | 2026-02-18 | 19
ORD-038 | Loom & Leaf | Hoodie | TOPS | 2000 | 2026-01-08 | 2026-02-08 | COMPLETE | COMPLETE | 2026-02-09 | 2026-02-09 | 1
ORD-049 | Harbor Knits | Scarf | ACCESSORIES | 300 | 2026-01-08 | 2026-01-22 | COMPLETE | COMPLETE | 2026-01-30 | 2026-01-30 | 8
ORD-105 | Cotton Club | Hoodie | TOPS | 200 | 2026-01-08 | 2026-02-10 | COMPLETE | COMPLETE | 2026-01-27 | 2026-01-27 | -14
ORD-094 | Maple & Co | Vest | TOPS | 800 | 2026-01-09 | 2026-02-03 | COMPLETE | COMPLETE | 2026-01-31 | 2026-01-31 | -3
ORD-028 | TrendCart | Beanie | ACCESSORIES | 150 | 2026-01-10 | 2026-01-26 | COMPLETE | COMPLETE | 2026-02-04 | 2026-02-04 | 9
ORD-100 | Northwind Apparel | Crewneck sweater | TOPS | 200 | 2026-01-10 | 2026-01-31 | COMPLETE | COMPLETE | 2026-02-04 | 2026-02-04 | 4
ORD-115 | TrendCart | Cardigan | TOPS | 2000 | 2026-01-10 | 2026-01-28 | COMPLETE | COMPLETE | 2026-02-28 | 2026-02-28 | 31
ORD-039 | UrbanThread | Cardigan | TOPS | 600 | 2026-01-11 | 2026-02-10 | COMPLETE | COMPLETE | 2026-02-10 | 2026-02-10 | 0
ORD-001 | Cotton Club | Beanie | ACCESSORIES | 1000 | 2026-01-12 | 2026-02-08 | COMPLETE | COMPLETE | 2026-02-10 | 2026-02-10 | 2
ORD-106 | UrbanThread | Crewneck sweater | TOPS | 100 | 2026-01-12 | 2026-02-11 | COMPLETE | COMPLETE | 2026-02-01 | 2026-02-01 | -10
ORD-089 | Maple & Co | Cardigan | TOPS | 1000 | 2026-01-13 | 2026-02-07 | COMPLETE | COMPLETE | 2026-02-15 | 2026-02-15 | 8
ORD-101 | Harbor Knits | Scarf | ACCESSORIES | 1200 | 2026-01-13 | 2026-01-27 | COMPLETE | COMPLETE | 2026-02-07 | 2026-02-07 | 11
ORD-052 | Harbor Knits | Hoodie | TOPS | 1200 | 2026-01-14 | 2026-02-13 | COMPLETE | COMPLETE | 2026-02-12 | 2026-02-12 | -1
ORD-009 | Maple & Co | Hoodie | TOPS | 500 | 2026-01-16 | 2026-02-12 | COMPLETE | COMPLETE | 2026-01-31 | 2026-01-31 | -12
ORD-026 | Cotton Club | Hoodie | TOPS | 800 | 2026-01-16 | 2026-01-31 | COMPLETE | COMPLETE | 2026-02-05 | 2026-02-05 | 5
ORD-065 | Loom & Leaf | Crewneck sweater | TOPS | 100 | 2026-01-16 | 2026-02-12 | COMPLETE | COMPLETE | 2026-02-01 | 2026-02-01 | -11
ORD-070 | Northwind Apparel | Beanie | ACCESSORIES | 1200 | 2026-01-16 | 2026-02-09 | COMPLETE | COMPLETE | 2026-02-09 | 2026-02-09 | 0
ORD-098 | Cotton Club | Hoodie | TOPS | 400 | 2026-01-16 | 2026-02-15 | COMPLETE | COMPLETE | 2026-02-06 | 2026-02-06 | -9
ORD-021 | TrendCart | Vest | TOPS | 800 | 2026-01-17 | 2026-02-18 | COMPLETE | COMPLETE | 2026-02-13 | 2026-02-13 | -5
ORD-056 | UrbanThread | Scarf | ACCESSORIES | 500 | 2026-01-17 | 2026-02-16 | COMPLETE | COMPLETE | 2026-02-03 | 2026-02-03 | -13
ORD-102 | Loom & Leaf | Beanie | ACCESSORIES | 600 | 2026-01-19 | 2026-02-12 | COMPLETE | COMPLETE | 2026-02-12 | 2026-02-12 | 0
ORD-006 | Northwind Apparel | Vest | TOPS | 150 | 2026-01-20 | 2026-02-20 | COMPLETE | COMPLETE | 2026-02-04 | 2026-02-04 | -16
ORD-064 | Loom & Leaf | Beanie | ACCESSORIES | 400 | 2026-01-20 | 2026-02-21 | COMPLETE | COMPLETE | 2026-02-09 | 2026-02-09 | -12
ORD-116 | Cotton Club | Cardigan | TOPS | 600 | 2026-01-21 | 2026-02-20 | COMPLETE | COMPLETE | 2026-02-11 | 2026-02-11 | -9
ORD-059 | TrendCart | Scarf | ACCESSORIES | 100 | 2026-01-22 | 2026-02-24 | COMPLETE | COMPLETE | 2026-02-15 | 2026-02-15 | -9
ORD-090 | TrendCart | Polo shirt | TOPS | 600 | 2026-01-22 | 2026-02-23 | COMPLETE | COMPLETE | 2026-03-06 | 2026-03-06 | 11
ORD-018 | Maple & Co | Beanie | ACCESSORIES | 1200 | 2026-01-23 | 2026-02-18 | COMPLETE | COMPLETE | 2026-02-27 | 2026-02-27 | 9
ORD-078 | Bright Basics | Beanie | ACCESSORIES | 300 | 2026-01-23 | 2026-02-14 | COMPLETE | COMPLETE | 2026-02-11 | 2026-02-11 | -3
ORD-086 | Bright Basics | Hoodie | TOPS | 300 | 2026-01-23 | 2026-02-11 | COMPLETE | COMPLETE | 2026-02-09 | 2026-02-09 | -2
ORD-022 | Maple & Co | Hoodie | TOPS | 800 | 2026-01-25 | 2026-02-21 | COMPLETE | COMPLETE | 2026-02-24 | 2026-02-24 | 3
ORD-051 | Maple & Co | Hoodie | TOPS | 200 | 2026-01-25 | 2026-02-19 | COMPLETE | COMPLETE | 2026-02-09 | 2026-02-09 | -10
ORD-003 | Maple & Co | Beanie | ACCESSORIES | 1200 | 2026-01-27 | 2026-02-17 | COMPLETE | COMPLETE | 2026-02-27 | 2026-02-27 | 10
ORD-014 | TrendCart | Vest | TOPS | 2000 | 2026-01-27 | 2026-02-28 | COMPLETE | COMPLETE | 2026-03-23 | 2026-03-23 | 23
ORD-118 | UrbanThread | Cardigan | TOPS | 100 | 2026-01-29 | 2026-03-02 | COMPLETE | COMPLETE | 2026-02-10 | 2026-02-10 | -20
ORD-067 | Harbor Knits | Hoodie | TOPS | 400 | 2026-01-30 | 2026-03-04 | COMPLETE | COMPLETE | 2026-02-15 | 2026-02-15 | -17
ORD-071 | Loom & Leaf | Scarf | ACCESSORIES | 1200 | 2026-01-30 | 2026-03-04 | COMPLETE | COMPLETE | 2026-02-25 | 2026-02-25 | -7
ORD-004 | Bright Basics | Cardigan | TOPS | 500 | 2026-01-31 | 2026-03-07 | COMPLETE | COMPLETE | 2026-02-27 | 2026-02-27 | -8
ORD-058 | Maple & Co | Crewneck sweater | TOPS | 2000 | 2026-02-02 | 2026-02-20 | COMPLETE | COMPLETE | 2026-03-12 | 2026-03-12 | 20
ORD-072 | Maple & Co | Cardigan | TOPS | 600 | 2026-02-02 | 2026-02-27 | COMPLETE | COMPLETE | 2026-02-18 | 2026-02-18 | -9
ORD-043 | UrbanThread | Scarf | ACCESSORIES | 500 | 2026-02-03 | 2026-02-23 | COMPLETE | COMPLETE | 2026-02-21 | 2026-02-21 | -2
ORD-047 | Cotton Club | Vest | TOPS | 150 | 2026-02-03 | 2026-02-23 | COMPLETE | COMPLETE | 2026-02-22 | 2026-02-22 | -1
ORD-042 | Maple & Co | Scarf | ACCESSORIES | 400 | 2026-02-04 | 2026-03-05 | COMPLETE | COMPLETE | 2026-02-25 | 2026-02-25 | -8
ORD-085 | Harbor Knits | Vest | TOPS | 1500 | 2026-02-07 | 2026-03-01 | COMPLETE | COMPLETE | 2026-03-05 | 2026-03-05 | 4
ORD-119 | Maple & Co | Scarf | ACCESSORIES | 150 | 2026-02-08 | 2026-02-22 | COMPLETE | COMPLETE | 2026-02-27 | 2026-02-27 | 5
ORD-023 | Maple & Co | Hoodie | TOPS | 600 | 2026-02-09 | 2026-02-23 | COMPLETE | COMPLETE | 2026-03-03 | 2026-03-03 | 8
ORD-111 | Cotton Club | Crewneck sweater | TOPS | 2000 | 2026-02-09 | 2026-03-16 | COMPLETE | COMPLETE | 2026-03-22 | 2026-03-22 | 6
ORD-097 | Bright Basics | Cardigan | TOPS | 800 | 2026-02-10 | 2026-03-01 | COMPLETE | COMPLETE | 2026-03-09 | 2026-03-09 | 8
ORD-016 | Cotton Club | Hoodie | TOPS | 800 | 2026-02-11 | 2026-03-16 | COMPLETE | COMPLETE | 2026-03-08 | 2026-03-08 | -8
ORD-074 | Loom & Leaf | Scarf | ACCESSORIES | 300 | 2026-02-12 | 2026-03-12 | COMPLETE | COMPLETE | 2026-03-10 | 2026-03-10 | -2
ORD-011 | Maple & Co | Hoodie | TOPS | 1200 | 2026-02-13 | 2026-03-14 | COMPLETE | COMPLETE | 2026-03-12 | 2026-03-12 | -2
ORD-032 | Northwind Apparel | Beanie | ACCESSORIES | 1500 | 2026-02-13 | 2026-03-14 | COMPLETE | COMPLETE | 2026-03-17 | 2026-03-17 | 3
ORD-050 | Northwind Apparel | Vest | TOPS | 500 | 2026-02-13 | 2026-03-05 | COMPLETE | COMPLETE | 2026-02-28 | 2026-02-28 | -5
ORD-068 | Cotton Club | Cardigan | TOPS | 600 | 2026-02-13 | 2026-03-10 | COMPLETE | COMPLETE | 2026-03-04 | 2026-03-04 | -6
ORD-012 | Cotton Club | Vest | TOPS | 1200 | 2026-02-14 | 2026-03-09 | COMPLETE | COMPLETE | 2026-03-08 | 2026-03-08 | -1
ORD-013 | Northwind Apparel | Polo shirt | TOPS | 1000 | 2026-02-16 | 2026-03-03 | COMPLETE | COMPLETE | 2026-03-17 | 2026-03-17 | 14
ORD-034 | Harbor Knits | Cardigan | TOPS | 1000 | 2026-02-17 | 2026-03-12 | COMPLETE | COMPLETE | 2026-03-19 | 2026-03-19 | 7
ORD-048 | Northwind Apparel | Hoodie | TOPS | 200 | 2026-02-20 | 2026-03-25 | COMPLETE | COMPLETE | 2026-03-13 | 2026-03-13 | -12
ORD-054 | TrendCart | Vest | TOPS | 600 | 2026-02-20 | 2026-03-06 | COMPLETE | COMPLETE | 2026-03-29 | 2026-03-29 | 23
ORD-037 | Cotton Club | Vest | TOPS | 200 | 2026-02-23 | 2026-03-18 | COMPLETE | COMPLETE | 2026-03-20 | 2026-03-20 | 2
ORD-079 | Northwind Apparel | Crewneck sweater | TOPS | 300 | 2026-02-24 | 2026-03-30 | COMPLETE | COMPLETE | 2026-03-23 | 2026-03-23 | -7
ORD-092 | Maple & Co | Beanie | ACCESSORIES | 500 | 2026-02-24 | 2026-03-15 | COMPLETE | COMPLETE | 2026-03-19 | 2026-03-19 | 4
ORD-104 | UrbanThread | Vest | TOPS | 200 | 2026-02-24 | 2026-03-28 | COMPLETE | COMPLETE | 2026-03-11 | 2026-03-11 | -17
ORD-046 | UrbanThread | Hoodie | TOPS | 150 | 2026-02-25 | 2026-03-31 | COMPLETE | COMPLETE | 2026-03-09 | 2026-03-09 | -22
ORD-075 | UrbanThread | Crewneck sweater | TOPS | 400 | 2026-02-25 | 2026-03-28 | COMPLETE | COMPLETE | 2026-03-11 | 2026-03-11 | -17
ORD-120 | TrendCart | Vest | TOPS | 1500 | 2026-02-27 | 2026-03-17 | IN_PROGRESS | ASSEMBLY | 2026-03-30
ORD-027 | Loom & Leaf | Hoodie | TOPS | 600 | 2026-02-28 | 2026-03-19 | COMPLETE | COMPLETE | 2026-03-16 | 2026-03-16 | -3
ORD-030 | TrendCart | Cardigan | TOPS | 400 | 2026-02-28 | 2026-03-27 | COMPLETE | COMPLETE | 2026-03-28 | 2026-03-28 | 1
ORD-031 | Maple & Co | Crewneck sweater | TOPS | 300 | 2026-02-28 | 2026-03-31 | COMPLETE | COMPLETE | 2026-03-26 | 2026-03-26 | -5
ORD-033 | Bright Basics | Polo shirt | TOPS | 200 | 2026-03-01 | 2026-03-18 | COMPLETE | COMPLETE | 2026-03-15 | 2026-03-15 | -3
ORD-107 | Northwind Apparel | Cardigan | TOPS | 2000 | 2026-03-01 | 2026-03-16 | IN_PROGRESS | PACKING | 2026-04-01
ORD-113 | Bright Basics | Scarf | ACCESSORIES | 800 | 2026-03-01 | 2026-03-22 | COMPLETE | COMPLETE | 2026-03-26 | 2026-03-26 | 4
ORD-019 | Northwind Apparel | Vest | TOPS | 600 | 2026-03-02 | 2026-03-29 | COMPLETE | COMPLETE | 2026-03-29 | 2026-03-29 | 0
ORD-088 | Harbor Knits | Crewneck sweater | TOPS | 300 | 2026-03-02 | 2026-03-21 | COMPLETE | COMPLETE | 2026-03-18 | 2026-03-18 | -3
ORD-114 | Northwind Apparel | Hoodie | TOPS | 2000 | 2026-03-03 | 2026-03-23 | IN_PROGRESS | PACKING | 2026-03-30
ORD-002 | Cotton Club | Crewneck sweater | TOPS | 1000 | 2026-03-06 | 2026-03-29 | IN_PROGRESS | WASHING | 2026-03-23
ORD-044 | Cotton Club | Cardigan | TOPS | 500 | 2026-03-07 | 2026-04-06 | COMPLETE | COMPLETE | 2026-03-26 | 2026-03-26 | -11
ORD-083 | Maple & Co | Hoodie | TOPS | 1000 | 2026-03-07 | 2026-03-23 | IN_PROGRESS | WASHING | 2026-03-30
ORD-099 | Northwind Apparel | Polo shirt | TOPS | 1500 | 2026-03-07 | 2026-04-05 | IN_PROGRESS | WASHING | 2026-03-31
ORD-020 | TrendCart | Vest | TOPS | 1200 | 2026-03-08 | 2026-03-31 | IN_PROGRESS | WASHING | 2026-03-30
ORD-103 | Bright Basics | Scarf | ACCESSORIES | 2000 | 2026-03-09 | 2026-04-04 | IN_PROGRESS | ASSEMBLY | 2026-03-30
ORD-029 | Northwind Apparel | Beanie | ACCESSORIES | 1500 | 2026-03-10 | 2026-04-01 | IN_PROGRESS | WASHING | 2026-04-01
ORD-109 | Harbor Knits | Vest | TOPS | 500 | 2026-03-10 | 2026-04-13 | IN_PROGRESS | WASHING | 2026-03-30
ORD-069 | Harbor Knits | Cardigan | TOPS | 400 | 2026-03-11 | 2026-04-09 | COMPLETE | COMPLETE | 2026-03-30 | 2026-03-30 | -10
ORD-112 | Harbor Knits | Hoodie | TOPS | 300 | 2026-03-11 | 2026-03-28 | COMPLETE | COMPLETE | 2026-03-24 | 2026-03-24 | -4
ORD-060 | Maple & Co | Hoodie | TOPS | 300 | 2026-03-12 | 2026-04-01 | COMPLETE | COMPLETE | 2026-03-27 | 2026-03-27 | -5
ORD-061 | Harbor Knits | Scarf | ACCESSORIES | 800 | 2026-03-12 | 2026-04-05 | IN_PROGRESS | WASHING | 2026-03-30
ORD-084 | Maple & Co | Cardigan | TOPS | 500 | 2026-03-13 | 2026-04-01 | COMPLETE | COMPLETE | 2026-03-28 | 2026-03-28 | -4
ORD-093 | Maple & Co | Beanie | ACCESSORIES | 100 | 2026-03-14 | 2026-03-29 | IN_PROGRESS | WASHING | 2026-04-01
ORD-055 | Cotton Club | Crewneck sweater | TOPS | 800 | 2026-03-15 | 2026-03-31 | IN_PROGRESS | ASSEMBLY | 2026-04-01
ORD-108 | Harbor Knits | Scarf | ACCESSORIES | 2000 | 2026-03-17 | 2026-04-03 | IN_PROGRESS | ASSEMBLY | 2026-03-31
ORD-081 | Harbor Knits | Crewneck sweater | TOPS | 1500 | 2026-03-18 | 2026-04-13 | IN_PROGRESS | ASSEMBLY | 2026-03-30
ORD-041 | Harbor Knits | Beanie | ACCESSORIES | 600 | 2026-03-19 | 2026-04-21 | IN_PROGRESS | WASHING | 2026-04-01
ORD-096 | TrendCart | Beanie | ACCESSORIES | 1000 | 2026-03-19 | 2026-04-17 | IN_PROGRESS | KNITTING | 2026-04-01
ORD-005 | TrendCart | Scarf | ACCESSORIES | 500 | 2026-03-21 | 2026-04-20 | IN_PROGRESS | KNITTING | 2026-03-24
ORD-045 | Cotton Club | Vest | TOPS | 150 | 2026-03-21 | 2026-04-09 | IN_PROGRESS | WASHING | 2026-03-30
ORD-053 | UrbanThread | Polo shirt | TOPS | 800 | 2026-03-21 | 2026-04-10 | IN_PROGRESS | ASSEMBLY | 2026-03-31
ORD-073 | Loom & Leaf | Hoodie | TOPS | 400 | 2026-03-21 | 2026-04-20 | IN_PROGRESS | ASSEMBLY | 2026-03-31
ORD-036 | UrbanThread | Scarf | ACCESSORIES | 1000 | 2026-03-22 | 2026-04-26 | IN_PROGRESS | KNITTING | 2026-03-31
ORD-062 | Bright Basics | Scarf | ACCESSORIES | 2000 | 2026-03-22 | 2026-04-08 | IN_PROGRESS | KNITTING | 2026-03-31
ORD-066 | Northwind Apparel | Polo shirt | TOPS | 1000 | 2026-03-22 | 2026-04-26 | IN_PROGRESS | ASSEMBLY | 2026-03-30
ORD-008 | Loom & Leaf | Polo shirt | TOPS | 600 | 2026-03-23 | 2026-04-09 | IN_PROGRESS | KNITTING | 2026-03-31
ORD-015 | UrbanThread | Vest | TOPS | 300 | 2026-03-23 | 2026-04-16 | IN_PROGRESS | ASSEMBLY | 2026-03-30
ORD-017 | TrendCart | Cardigan | TOPS | 800 | 2026-03-23 | 2026-04-10 | IN_PROGRESS | KNITTING | 2026-04-01
ORD-010 | Cotton Club | Cardigan | TOPS | 1000 | 2026-03-24 | 2026-04-25 | IN_PROGRESS | KNITTING | 2026-03-30
ORD-024 | Loom & Leaf | Vest | TOPS | 300 | 2026-03-24 | 2026-04-15 | IN_PROGRESS | ASSEMBLY | 2026-04-01
ORD-035 | Loom & Leaf | Beanie | ACCESSORIES | 300 | 2026-03-25 | 2026-04-29 | IN_PROGRESS | KNITTING | 2026-04-01
ORD-040 | Loom & Leaf | Hoodie | TOPS | 1200 | 2026-03-25 | 2026-04-21 | IN_PROGRESS | KNITTING | 2026-04-01
ORD-063 | Loom & Leaf | Cardigan | TOPS | 100 | 2026-03-27 | 2026-04-29 | IN_PROGRESS | KNITTING | 2026-03-30
ORD-082 | TrendCart | Beanie | ACCESSORIES | 600 | 2026-03-27 | 2026-05-01 | IN_PROGRESS | KNITTING | 2026-03-30
ORD-095 | Bright Basics | Hoodie | TOPS | 800 | 2026-03-27 | 2026-04-26 | IN_PROGRESS | KNITTING | 2026-04-01

## production_log
date | stage | pieces_completed
2026-01-01 | KNITTING | 1027
2026-01-01 | ASSEMBLY | 836
2026-01-01 | WASHING | 795
2026-01-01 | PACKING | 699
2026-01-02 | KNITTING | 997
2026-01-02 | ASSEMBLY | 785
2026-01-02 | WASHING | 615
2026-01-02 | PACKING | 606
2026-01-03 | KNITTING | 811
2026-01-03 | ASSEMBLY | 718
2026-01-03 | WASHING | 643
2026-01-03 | PACKING | 568
2026-01-04 | KNITTING | 0
2026-01-04 | ASSEMBLY | 0
2026-01-04 | WASHING | 0
2026-01-04 | PACKING | 0
2026-01-05 | KNITTING | 861
2026-01-05 | ASSEMBLY | 773
2026-01-05 | WASHING | 601
2026-01-05 | PACKING | 595
2026-01-06 | KNITTING | 1017
2026-01-06 | ASSEMBLY | 734
2026-01-06 | WASHING | 598
2026-01-06 | PACKING | 670
2026-01-07 | KNITTING | 933
2026-01-07 | ASSEMBLY | 878
2026-01-07 | WASHING | 728
2026-01-07 | PACKING | 711
2026-01-08 | KNITTING | 790
2026-01-08 | ASSEMBLY | 719
2026-01-08 | WASHING | 765
2026-01-08 | PACKING | 566
2026-01-09 | KNITTING | 849
2026-01-09 | ASSEMBLY | 812
2026-01-09 | WASHING | 765
2026-01-09 | PACKING | 721
2026-01-10 | KNITTING | 947
2026-01-10 | ASSEMBLY | 751
2026-01-10 | WASHING | 632
2026-01-10 | PACKING | 611
2026-01-11 | KNITTING | 0
2026-01-11 | ASSEMBLY | 0
2026-01-11 | WASHING | 0
2026-01-11 | PACKING | 0
2026-01-12 | KNITTING | 1026
2026-01-12 | ASSEMBLY | 695
2026-01-12 | WASHING | 650
2026-01-12 | PACKING | 567
2026-01-13 | KNITTING | 988
2026-01-13 | ASSEMBLY | 881
2026-01-13 | WASHING | 612
2026-01-13 | PACKING | 566
2026-01-14 | KNITTING | 838
2026-01-14 | ASSEMBLY | 734
2026-01-14 | WASHING | 609
2026-01-14 | PACKING | 610
2026-01-15 | KNITTING | 853
2026-01-15 | ASSEMBLY | 752
2026-01-15 | WASHING | 710
2026-01-15 | PACKING | 724
2026-01-16 | KNITTING | 806
2026-01-16 | ASSEMBLY | 738
2026-01-16 | WASHING | 733
2026-01-16 | PACKING | 610
2026-01-17 | KNITTING | 1012
2026-01-17 | ASSEMBLY | 823
2026-01-17 | WASHING | 636
2026-01-17 | PACKING | 674
2026-01-18 | KNITTING | 0
2026-01-18 | ASSEMBLY | 0
2026-01-18 | WASHING | 0
2026-01-18 | PACKING | 0
2026-01-19 | KNITTING | 902
2026-01-19 | ASSEMBLY | 685
2026-01-19 | WASHING | 732
2026-01-19 | PACKING | 613
2026-01-20 | KNITTING | 929
2026-01-20 | ASSEMBLY | 825
2026-01-20 | WASHING | 762
2026-01-20 | PACKING | 722
2026-01-21 | KNITTING | 987
2026-01-21 | ASSEMBLY | 841
2026-01-21 | WASHING | 668
2026-01-21 | PACKING | 624
2026-01-22 | KNITTING | 793
2026-01-22 | ASSEMBLY | 908
2026-01-22 | WASHING | 765
2026-01-22 | PACKING | 727
2026-01-23 | KNITTING | 874
2026-01-23 | ASSEMBLY | 707
2026-01-23 | WASHING | 649
2026-01-23 | PACKING | 659
2026-01-24 | KNITTING | 786
2026-01-24 | ASSEMBLY | 690
2026-01-24 | WASHING | 656
2026-01-24 | PACKING | 695
2026-01-25 | KNITTING | 0
2026-01-25 | ASSEMBLY | 0
2026-01-25 | WASHING | 0
2026-01-25 | PACKING | 0
2026-01-26 | KNITTING | 961
2026-01-26 | ASSEMBLY | 735
2026-01-26 | WASHING | 680
2026-01-26 | PACKING | 735
2026-01-27 | KNITTING | 959
2026-01-27 | ASSEMBLY | 713
2026-01-27 | WASHING | 749
2026-01-27 | PACKING | 599
2026-01-28 | KNITTING | 801
2026-01-28 | ASSEMBLY | 890
2026-01-28 | WASHING | 686
2026-01-28 | PACKING | 746
2026-01-29 | KNITTING | 791
2026-01-29 | ASSEMBLY | 703
2026-01-29 | WASHING | 718
2026-01-29 | PACKING | 626
2026-01-30 | KNITTING | 937
2026-01-30 | ASSEMBLY | 895
2026-01-30 | WASHING | 776
2026-01-30 | PACKING | 737
2026-01-31 | KNITTING | 837
2026-01-31 | ASSEMBLY | 766
2026-01-31 | WASHING | 711
2026-01-31 | PACKING | 567
2026-02-01 | KNITTING | 0
2026-02-01 | ASSEMBLY | 0
2026-02-01 | WASHING | 0
2026-02-01 | PACKING | 0
2026-02-02 | KNITTING | 765
2026-02-02 | ASSEMBLY | 847
2026-02-02 | WASHING | 623
2026-02-02 | PACKING | 589
2026-02-03 | KNITTING | 854
2026-02-03 | ASSEMBLY | 807
2026-02-03 | WASHING | 720
2026-02-03 | PACKING | 723
2026-02-04 | KNITTING | 868
2026-02-04 | ASSEMBLY | 777
2026-02-04 | WASHING | 716
2026-02-04 | PACKING | 721
2026-02-05 | KNITTING | 876
2026-02-05 | ASSEMBLY | 785
2026-02-05 | WASHING | 769
2026-02-05 | PACKING | 587
2026-02-06 | KNITTING | 781
2026-02-06 | ASSEMBLY | 736
2026-02-06 | WASHING | 790
2026-02-06 | PACKING | 689
2026-02-07 | KNITTING | 882
2026-02-07 | ASSEMBLY | 918
2026-02-07 | WASHING | 668
2026-02-07 | PACKING | 689
2026-02-08 | KNITTING | 0
2026-02-08 | ASSEMBLY | 0
2026-02-08 | WASHING | 0
2026-02-08 | PACKING | 0
2026-02-09 | KNITTING | 990
2026-02-09 | ASSEMBLY | 754
2026-02-09 | WASHING | 770
2026-02-09 | PACKING | 662
2026-02-10 | KNITTING | 967
2026-02-10 | ASSEMBLY | 696
2026-02-10 | WASHING | 774
2026-02-10 | PACKING | 734
2026-02-11 | KNITTING | 801
2026-02-11 | ASSEMBLY | 702
2026-02-11 | WASHING | 645
2026-02-11 | PACKING | 633
2026-02-12 | KNITTING | 866
2026-02-12 | ASSEMBLY | 859
2026-02-12 | WASHING | 752
2026-02-12 | PACKING | 609
2026-02-13 | KNITTING | 818
2026-02-13 | ASSEMBLY | 702
2026-02-13 | WASHING | 797
2026-02-13 | PACKING | 562
2026-02-14 | KNITTING | 1004
2026-02-14 | ASSEMBLY | 779
2026-02-14 | WASHING | 801
2026-02-14 | PACKING | 635
2026-02-15 | KNITTING | 0
2026-02-15 | ASSEMBLY | 0
2026-02-15 | WASHING | 0
2026-02-15 | PACKING | 0
2026-02-16 | KNITTING | 852
2026-02-16 | ASSEMBLY | 875
2026-02-16 | WASHING | 730
2026-02-16 | PACKING | 723
2026-02-17 | KNITTING | 922
2026-02-17 | ASSEMBLY | 786
2026-02-17 | WASHING | 685
2026-02-17 | PACKING | 562
2026-02-18 | KNITTING | 862
2026-02-18 | ASSEMBLY | 715
2026-02-18 | WASHING | 764
2026-02-18 | PACKING | 700
2026-02-19 | KNITTING | 864
2026-02-19 | ASSEMBLY | 727
2026-02-19 | WASHING | 618
2026-02-19 | PACKING | 697
2026-02-20 | KNITTING | 883
2026-02-20 | ASSEMBLY | 710
2026-02-20 | WASHING | 618
2026-02-20 | PACKING | 573
2026-02-21 | KNITTING | 885
2026-02-21 | ASSEMBLY | 687
2026-02-21 | WASHING | 793
2026-02-21 | PACKING | 554
2026-02-22 | KNITTING | 0
2026-02-22 | ASSEMBLY | 0
2026-02-22 | WASHING | 0
2026-02-22 | PACKING | 0
2026-02-23 | KNITTING | 974
2026-02-23 | ASSEMBLY | 720
2026-02-23 | WASHING | 685
2026-02-23 | PACKING | 724
2026-02-24 | KNITTING | 1018
2026-02-24 | ASSEMBLY | 711
2026-02-24 | WASHING | 668
2026-02-24 | PACKING | 702
2026-02-25 | KNITTING | 786
2026-02-25 | ASSEMBLY | 706
2026-02-25 | WASHING | 756
2026-02-25 | PACKING | 560
2026-02-26 | KNITTING | 1009
2026-02-26 | ASSEMBLY | 725
2026-02-26 | WASHING | 649
2026-02-26 | PACKING | 711
2026-02-27 | KNITTING | 994
2026-02-27 | ASSEMBLY | 725
2026-02-27 | WASHING | 715
2026-02-27 | PACKING | 742
2026-02-28 | KNITTING | 1032
2026-02-28 | ASSEMBLY | 808
2026-02-28 | WASHING | 647
2026-02-28 | PACKING | 744
2026-03-01 | KNITTING | 0
2026-03-01 | ASSEMBLY | 0
2026-03-01 | WASHING | 0
2026-03-01 | PACKING | 0
2026-03-02 | KNITTING | 767
2026-03-02 | ASSEMBLY | 782
2026-03-02 | WASHING | 780
2026-03-02 | PACKING | 676
2026-03-03 | KNITTING | 852
2026-03-03 | ASSEMBLY | 687
2026-03-03 | WASHING | 728
2026-03-03 | PACKING | 707
2026-03-04 | KNITTING | 907
2026-03-04 | ASSEMBLY | 901
2026-03-04 | WASHING | 702
2026-03-04 | PACKING | 721
2026-03-05 | KNITTING | 868
2026-03-05 | ASSEMBLY | 762
2026-03-05 | WASHING | 680
2026-03-05 | PACKING | 676
2026-03-06 | KNITTING | 1011
2026-03-06 | ASSEMBLY | 733
2026-03-06 | WASHING | 790
2026-03-06 | PACKING | 722
2026-03-07 | KNITTING | 999
2026-03-07 | ASSEMBLY | 912
2026-03-07 | WASHING | 798
2026-03-07 | PACKING | 682
2026-03-08 | KNITTING | 0
2026-03-08 | ASSEMBLY | 0
2026-03-08 | WASHING | 0
2026-03-08 | PACKING | 0
2026-03-09 | KNITTING | 878
2026-03-09 | ASSEMBLY | 770
2026-03-09 | WASHING | 598
2026-03-09 | PACKING | 642
2026-03-10 | KNITTING | 797
2026-03-10 | ASSEMBLY | 761
2026-03-10 | WASHING | 737
2026-03-10 | PACKING | 605
2026-03-11 | KNITTING | 924
2026-03-11 | ASSEMBLY | 855
2026-03-11 | WASHING | 740
2026-03-11 | PACKING | 662
2026-03-12 | KNITTING | 837
2026-03-12 | ASSEMBLY | 755
2026-03-12 | WASHING | 671
2026-03-12 | PACKING | 679
2026-03-13 | KNITTING | 772
2026-03-13 | ASSEMBLY | 799
2026-03-13 | WASHING | 711
2026-03-13 | PACKING | 714
2026-03-14 | KNITTING | 768
2026-03-14 | ASSEMBLY | 763
2026-03-14 | WASHING | 602
2026-03-14 | PACKING | 619
2026-03-15 | KNITTING | 0
2026-03-15 | ASSEMBLY | 0
2026-03-15 | WASHING | 0
2026-03-15 | PACKING | 0
2026-03-16 | KNITTING | 867
2026-03-16 | ASSEMBLY | 788
2026-03-16 | WASHING | 679
2026-03-16 | PACKING | 631
2026-03-17 | KNITTING | 909
2026-03-17 | ASSEMBLY | 735
2026-03-17 | WASHING | 617
2026-03-17 | PACKING | 638
2026-03-18 | KNITTING | 960
2026-03-18 | ASSEMBLY | 882
2026-03-18 | WASHING | 723
2026-03-18 | PACKING | 707
2026-03-19 | KNITTING | 956
2026-03-19 | ASSEMBLY | 868
2026-03-19 | WASHING | 701
2026-03-19 | PACKING | 708
2026-03-20 | KNITTING | 867
2026-03-20 | ASSEMBLY | 762
2026-03-20 | WASHING | 628
2026-03-20 | PACKING | 627
2026-03-21 | KNITTING | 871
2026-03-21 | ASSEMBLY | 746
2026-03-21 | WASHING | 721
2026-03-21 | PACKING | 561
2026-03-22 | KNITTING | 0
2026-03-22 | ASSEMBLY | 0
2026-03-22 | WASHING | 0
2026-03-22 | PACKING | 0
2026-03-23 | KNITTING | 891
2026-03-23 | ASSEMBLY | 733
2026-03-23 | WASHING | 757
2026-03-23 | PACKING | 667
2026-03-24 | KNITTING | 992
2026-03-24 | ASSEMBLY | 779
2026-03-24 | WASHING | 741
2026-03-24 | PACKING | 671
2026-03-25 | KNITTING | 915
2026-03-25 | ASSEMBLY | 394
2026-03-25 | WASHING | 801
2026-03-25 | PACKING | 658
2026-03-26 | KNITTING | 1033
2026-03-26 | ASSEMBLY | 464
2026-03-26 | WASHING | 801
2026-03-26 | PACKING | 673
2026-03-27 | KNITTING | 882
2026-03-27 | ASSEMBLY | 399
2026-03-27 | WASHING | 793
2026-03-27 | PACKING | 580
2026-03-28 | KNITTING | 1031
2026-03-28 | ASSEMBLY | 445
2026-03-28 | WASHING | 624
2026-03-28 | PACKING | 734
2026-03-29 | KNITTING | 0
2026-03-29 | ASSEMBLY | 0
2026-03-29 | WASHING | 0
2026-03-29 | PACKING | 0
2026-03-30 | KNITTING | 829
2026-03-30 | ASSEMBLY | 396
2026-03-30 | WASHING | 605
2026-03-30 | PACKING | 625
2026-03-31 | KNITTING | 905
2026-03-31 | ASSEMBLY | 455
2026-03-31 | WASHING | 732
2026-03-31 | PACKING | 657

## workshops
workshop_id | name | capacity_pieces_per_day | pickup_lead_days | defect_rate | cost_per_piece | makes | status | max_batch_pieces | current_queue_days | notes
W1 | QuickStitch | 300 | 1 | 0.12 | 1.5 | TOPS | ACTIVE |  | 4 | fastest in the region; quality slips under pressure
W2 | SteadyHands | 170 | 2 | 0.03 | 1.3 | TOPS+ACCESSORIES | ACTIVE |  | 2.5 | never early, never late, never sloppy
W3 | BudgetWorks | 230 | 3 | 0.09 | 0.8 | TOPS | ACTIVE |  | 5 | cheapest by far
W4 | Little Loom | 70 | 1 | 0.02 | 1.6 | ACCESSORIES | ACTIVE |  | 0.5 | tiny boutique shop, immaculate work
W5 | GiantWeave | 400 | 4 | 0.06 | 1.1 | TOPS | ACTIVE |  | 3 | huge capacity, slow pickup and delivery
W6 | Nimble Needle | 130 | 1 | 0.05 | 1.2 | TOPS+ACCESSORIES | ACTIVE |  | 1 | quick turnaround on small batches
W7 | OldMill | 200 | 2 | 0.1 | 0.9 | TOPS+ACCESSORIES | SUSPENDED |  | 0 | suspended after last month's quality audit
W8 | FreshStart | 100 | 2 | 0.04 | 1 | TOPS | ACTIVE | 300 | 0 | new workshop on trial: small batches only